## ROC Claimant VW260567 (2)
Record of Claim - Claim Number VW260567 (2)
| Claimant Name: | Warcup, Graeme Curtis |  |  |  |  | Warranty Expiry Dates:
| Address: | 162, 2350 165 Street, Surrey, British Columbia, V3Z 1J9 |  |  |  |  | Defects in Labour and Material (1): |  | Mar 27, 2026
| Warranty Number | 80344542 |  |  |  |  | Defects in Labour and Material (2): |  | Mar 27, 2027
| Warranty Type: | Unit |  |  |  |  | Building Envelope: |  | N/A
| Builder: | Gramercy Grandview Developments Ltd. |  |  |  |  | Structural Defect: |  | N/A
| Last update by: | Maddison Plummer
| Last update: | Apr 02, 2026
Item Number | Date Submitted to Travelers | Location/Room | Description Of Claim | Reference Doc | Builder Comments | Travelers Canada Comments | Travelers Canada Position | Status | Date Item Resolved
1 | 2026-03-27 | Dining Room | Dining room drywall seam. NHWS - Drywall Seems-Bulging | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
2 | 2026-03-27 | Dining Room | Dining room nail pops | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
3 | 2026-03-27 | Upper Stairs | Cracks | As per NOC dated 03/27/2026 |  | Please provide more information and specific location of the defect noted. | Not Warrantable - see comments | Denied | 2026-04-02
4 | 2026-03-27 | Living Room | Nail pop living room behind couch | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
5 | 2026-03-27 | Kitchen | Minor cracks at the corners of doors and windows in walls. Appeared to be the result of settling. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
6 | 2026-03-27 | Jr Bedroom | Minor cracks at the corners of doors and windows in walls. Appeared to be the result of settling. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
7 | 2026-03-27 | Upper Stairs | Upstairs office walls Drywall Screw Pops. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
8 | 2026-03-27 | Kitchen | Kitchen wall Drywall Screw Pops. Interior finished drywall (excluding garages and unfinished areas), shall be free from nail/screw. pops that have broken the finished surface or are in a readily noticeable location. All work should be performed by a qualified drywall or painting contractor. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
9 | 2026-03-27 | Lower Stairs | Lower stairs wall Drywall Screw Pops. Interior finished drywall (excluding garages and unfinished areas), shall be free from nail/screw. pops that have broken the finished surface or are in a readily noticeable location. All work should be performed by a qualified drywall or painting contractor. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
10 | 2026-03-27 | Lower Stairs | Lower stairs wall cracks | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
11 | 2026-03-27 | Upper Stairs | Primary bedroom left of window screw pop from ceilings. Protruding screw heads visible at the time of the inspection appeared to be the result of contact with moisture. After the source of moisture is located and corrected, protruding screws should be removed, drywall re-fastened and the drywall finished to match the existing wall surfaces. All work should be performed by a qualified drywall or painting contractor. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
12 | 2026-03-27 | Entry | Over front door screw pop from ceilings. Protruding screw heads visible at the time of the inspection appeared to be the result of contact with moisture. After the source of moisture is located and corrected, protruding screws should be removed, drywall re-fastened and the drywall finished to match the existing wall surfaces. All work should be performed by a qualified drywall or painting contractor. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
13 | 2026-03-27 | Jr Bedroom | jr bed/garage entry screw pop from ceilings. Protruding screw heads visible at the time of the inspection appeared to be the result of contact with moisture. After the source of moisture is located and corrected, protruding screws should be removed, drywall re-fastened and the drywall finished to match the existing wall surfaces. All work should be performed by a qualified drywall or painting contractor. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
14 | 2026-03-27 | Upper Stairs | Upstairs office ceiling/wall joint separation - often referred to as truss uplift. The junction of inside wall finishes and ceilings should be constructed to minimize excessive cracking or wall/ceiling separation. Truss uplift is a term often applied to a condition where the bottom chord of wood roof trusses bow or arch upward causing the ceiling drywall that is fastened to it to become separated from the wall finish. Differences in the temperature and moisture content between the top and bottom members of trusses can cause seasonal movement of the bottom chord. The condition cannot always be prevented but can be controlled by good design, good attic venting and by "floating" the ceiling drywall near partitions. Similar damage can occur due to downward movement of the wall as a result of settlement of interior wall footings or shrinkage of the framing lumber. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
15 | 2026-03-27 | Upper Stairs | Primary bedroom ceiling/wall joint separation - often referred to as truss uplift. The junction of inside wall finishes and ceilings should be constructed to minimize excessive cracking or wall/ceiling separation. Truss uplift is a term often applied to a condition where the bottom chord of wood roof trusses bow or arch upward causing the ceiling drywall that is fastened to it to become separated from the wall finish. Differences in the temperature and moisture content between the top and bottom members of trusses can cause seasonal movement of the bottom chord. The condition cannot always be prevented but can be controlled by good design, good attic venting and by "floating" the ceiling drywall near partitions. Similar damage can occur due to downward movement of the wall as a result of settlement of interior wall footings or shrinkage of the framing lumber. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
16 | 2026-03-27 | Kitchen | Gap between cabinets and ceilings or walls. During the inspection, a noticeable gap was observed between the cabinets and the ceiling or walls in the kitchen. This could potentially indicate settling or improper installation. It is recommended to have a qualified contractor assess the situation and provide necessary repairs to ensure proper alignment and aesthetics. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
17 | 2026-03-27 | Upper Stairs | Secondary bathroom upstairs Tub / Shower Glazing Damaged. Visible chipping, which may lead to water infiltration and potential damage to the underlying material. It is recommended to repair the chipped area with an appropriate bathtub repair kit to prevent further deterioration. Consider consulting a professional if the damage extends beyond the visible surface. Damage has been there since we moved in. | As per NOC dated 03/27/2026 |  | Damage reported after occupation. Please provide your Pre-Delivery form and we will reassess coverage if item is listed. | Not Warrantable - see comments | Denied | 2026-04-02
18 | 2026-03-27 | Upper Stairs | Upstairs office Outlet or Switch Cover Plate Not Flush with wall. In finished areas, electrical receptacles/switches shall be installed so that the cover plates are generally flush with the adjacent wall surface. Electrical fixtures not meeting the Acceptable Performance/Condition must be rectified. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
19 | 2026-03-27 | Dining Room | Dining room stairs crew pop from ceilings. Protruding screw heads visible at the time of the inspection appeared to be the result of contact with moisture. After the source of moisture is located and corrected, protruding screws should be removed, drywall re-fastened and the drywall finished to match the existing wall surfaces. All work should be performed by a qualified drywall or painting contractor. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
20 | 2026-03-27 | Dining Room | Settlement cracks | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
21 | 2026-03-27 | Dining Room | Poor paint job | As per NOC dated 03/27/2026 |  | Insufficient information to determine warrantability. Please provide specific details including: location of paint defect, nature of the defect (e.g., peeling, blistering, drips, uneven coverage, missed areas)"Poor paint job" alone does not constitute sufficient particulars to evaluate the claim under the warranty policy. | Not Warrantable - see comments | Denied | 2026-04-02
22 | 2026-03-27 | Dining Room | Wall screw not filled in properly | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
23 | 2026-03-27 | Kitchen | Settlement cracks | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
24 | 2026-03-27 | Upper Stairs | Upstairs primary bathroom screw pop | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
25 | 2026-03-27 | Upper Stairs | Bathroom water damage, no sealing around this area | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
26 | 2026-03-27 | Upper Stairs | Primary bathroom grout missing | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
27 | 2026-03-27 | Upper Stairs | Small holes, wasn't filled in and sanded. small holes, wasn't filled in and sanded. Primary bedroom above closet. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
28 | 2026-03-27 | Upper Stairs | Primary bedroom above windows screw not filled in | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
29 | 2026-03-27 | Upper Stairs | Primary bedroom light switch no sanding, didn't fill properly | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
30 | 2026-03-27 | Upper Stairs | Upstairs office bedroom screw pops | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
31 | 2026-03-27 | Bath 2 | Plumbing - Toilet - Elongated/AA-2186. Since the day we moved in I've noticed this back speckle on the front of the toilet. I thought it was just dirty, but I haven't been able to get it off all year. This was is cosmetic damage caused during install or storage. | As per NOC dated 03/27/2026 |  | Damage reported after occupation. Please provide your Pre-Delivery form and we will reassess coverage if item is listed. | Not Warrantable - see comments | Denied | 2026-04-02
32 | 2026-03-27 | Kitchen | Appliances - Dishwasher - GBT640SMPES. Not sure if this is expected, but the dishwasher always have a lot of water in the food trap. It never fully drains. I didn't think anything of it until a neighbour mentioned they didn't have this issue. | As per NOC dated 03/27/2026 |  | Appliances are not covered under the New Home Warranty as they carry their own manufacturer's warranty. Please contact the appliance supplier/manufacturer directly to submit your claim. | Outside Scope of Warranty Policy | Denied | 2026-04-02
33 | 2026-03-27 | Dining Room | Screw pop on ceiling near staircase. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
34 | 2026-03-27 | Dining Room | Ceiling not sanded properly. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
35 | 2026-03-27 | Ensuite | Primary En Suite Bathroom. Ceiling Finishings Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting. Rough patch and not sanded properly. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
36 | 2026-03-27 | Other | Primary bedroom over bed. Ceiling Finishings Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting. Rough patch and not sanded properly. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
37 | 2026-03-27 | Upper Stairs | Top of stairs by the laundry room. Ceiling Finishings Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting. Rough patch and not sanded properly. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
38 | 2026-03-27 | Other | Bottom floor bathroom. Ceiling Finishings Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting. Rough patch and not sanded properly. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
39 | 2026-03-27 | Bath 2 | Shared bathroom upstairs. Ceiling Finishings Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting. Rough patch and not sanded properly. Painting is completely uneven. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
40 | 2026-03-27 | Upper Stairs | Top of staircase by master bedroom entrance. Ceiling Finishings Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
41 | 2026-03-27 | Top of staircase Ceiling | Top of staircase Ceiling Finishings - Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
42 | 2026-03-27 | Upstairs secondary bathroom ceiling | Upstairs secondary Bathroom Ceiling Finishings - Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
43 | 2026-03-27 | Living room | Drywall Seems-Bulging / Trowel Marks. Drywall surface blemishes including blisters in taped joints, trowel marks, excess joint compound and dents or gouges Conditions such as cracks, blisters in taped joints, trowel marks, excess joint compound, dents or tool gouges, that are readily noticeable | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
44 | 2026-03-27 | Lower stairway | Drywall -Minor Corner Crack - Interior finished drywall (excluding garages and unfinished areas), shall be free from nail/screw pops that have broken the finished surface or are in a readily noticeable location. All work should be performed by a qualified drywall or painting contractor. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
45 | 2026-03-27 | Kitchen/dining room walls | Interior finished drywall (excluding garages and unfinished areas), shall be free from nail/screw pops that have broken the finished surface or are in a readily noticeable location. All work should be performed by a qualified drywall or painting contractor. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
46 | 2026-03-27 | Upstairs office. | Interior finished drywall (excluding garages and unfinished areas), shall be free from nail/screw pops that have broken the finished surface or are in a readily noticeable location. All work should be performed by a qualified drywall or painting contractor. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
47 | 2026-03-27 | Kitchen/dining room walls | A properly painted surface (has consistent colour, appearance and cover) shall be provided on every exposed surface where a painted finish is specified and free from tool marks. | As per NOC dated 03/27/2026 |  | Insufficient information to determine warrantability. Please provide specific details of defect noted. | Not Warrantable - no defect noted | Denied | 2026-04-02
48 | 2026-03-27 | Upper staircase walls | A properly painted surface (has consistent colour, appearance and cover) shall be provided on every exposed surface where a painted finish is specified and free from tool marks. | As per NOC dated 03/27/2026 |  | Insufficient information to determine warrantability. Please provide specific details of defect noted. | Not Warrantable - no defect noted | Denied | 2026-04-02
49 | 2026-03-27 | Primary ensuite bathroom entrance | Sub standard painted surface. A properly painted surface (has consistent colour, appearance and cover) shall be provided on every exposed surface where a painted finish is specified and free from tool marks. Paint drips and tool marks over trim. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
50 | 2026-03-27 | Over laundry room door | Over laundry room door. Sub standard painted surface. A properly painted surface (has consistent colour, appearance and cover) shall be provided on every exposed surface where a painted finish is specified and free from tool marks. Paint drips and tool marks over trim. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
51 | 2026-03-27 | Garage | Garage closet door not pained on all 6 sides. | As per NOC dated 03/27/2026 |  | Missing or incomplete work is not covered under the policy. | Outside Scope of Warranty Policy | Denied | 2026-04-02
52 | 2026-03-27 | Garage entrance | Garage door not painted on all 6 sides. | As per NOC dated 03/27/2026 |  | Missing or incomplete work is not covered under the policy. |  | New
53 | 2026-03-27 | Jr. Bathroom | Jr bathroom door not pained on all 6 sides. | As per NOC dated 03/27/2026 |  | Missing or incomplete work is not covered under the policy. |  | New
54 | 2026-03-27 | Main floor closet | Main floor upstairs closet doors not painted on all 6 sides. | As per NOC dated 03/27/2026 |  | Missing or incomplete work is not covered under the policy. |  | New
55 | 2026-03-27 | Top floor | Washer/dryer doors not painted on all 6 sides. | As per NOC dated 03/27/2026 |  | Missing or incomplete work is not covered under the policy. |  | New
56 | 2026-03-27 | Secondary bedroom upstairs | Second upstairs bedroom door not painted on all 6 sides. | As per NOC dated 03/27/2026 |  | Missing or incomplete work is not covered under the policy. |  | New
57 | 2026-03-27 | Secondary washroom upstairs | Upstairs bathroom door not painted on all 6 sides. | As per NOC dated 03/27/2026 |  | Missing or incomplete work is not covered under the policy. |  | New
58 | 2026-03-27 | Master bedroom upstairs | Master bathroom door not painted on all 6 sides. | As per NOC dated 03/27/2026 |  | Missing or incomplete work is not covered under the policy. |  | New
59 | 2026-03-27 | Front door entrance | NHWS- Floors Springy & / or Shake. Front door entry - Movement occurring is beyond what is considered normal. | As per NOC dated 03/27/2026 |  | Concern related to Common Property. Please notify your Strata and the Strata can place the claim with Travelers under the Common Property Warranty. | Outside Scope - Concern related to Common Property | Denied | 2026-04-02
60 | 2026-03-27 | Jr. Bathroom | NHWS- Floors Springy & / or Shake - Downstairs Bathroom - All structural members including beams and joists must be sized, installed and fastened in accordance with the Building Code. Movement occurring is beyond what is considered normal. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
61 | 2026-03-27 | Living room | In Front of TV - All structural members including beams and joists must be sized, installed and fastened in accordance with the Building Code. Movement occurring is beyond what is considered normal. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
62 | 2026-03-27 | Living room sliding door trim | Cracked Window Trim. The crack to the window drip appears to have been caused by the screws for blind installation. The window trim is cracked, which may affect the aesthetics and potentially lead to further deterioration if not addressed. It is recommended to repair or replace the damaged trim to prevent possible moisture intrusion and maintain the integrity of the window area. | As per NOC dated 03/27/2026 |  | Concern related to Common Property. Please notify your Strata and the Strata can place the claim with Travelers under the Common Property Warranty. | Outside Scope - Concern related to Common Property | Denied | 2026-04-02
63 | 2026-03-27 | Upstairs secondary bedroom | Door ding in secondary bedroom. | As per NOC dated 03/27/2026 |  | Damage reported after occupation. Please provide your Pre-Delivery form and we will reassess coverage if item is listed. | Not Warrantable - see comments | Denied | 2026-04-02
64 | 2026-03-27 | Kitchen corner beside dishwasher. | Laminate flooring, separating at joints. The laminate flooring throughout the inspected area is exhibiting separation at the joints, which may affect the overall appearance and functionality of the flooring. This condition may result from changes in humidity, improper installation, or subfloor issues. It is recommended to consult with a flooring specialist to assess the extent of the problem and determine if resealing, reinstallation, or replacement is necessary to prevent further damage and ensure the flooring's longevity. Regular monitoring and maintaining stable humidity levels can help mitigate future issues. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
65 | 2026-03-27 | Kitchen floor in front of dishwasher | NHWS- Floors Springy & / or Shake. In front of Dishwasher - Movement occurring is beyond what is considered normal. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
66 | 2026-03-27 | Master bedroom door | Door chipped by repair performed by Daryl to resolve "door not closing" issue. | As per NOC dated 03/27/2026 |  | Damage reported after occupancy is not covered under the policy. | Outside Scope of Warranty Policy | Denied | 2026-04-02
67 | 2026-03-27 | Upstairs office | Sub standard painted surface. | As per NOC dated 03/27/2026 |  | Insufficient information to determine warrantability. Please provide specific details including: location of paint defect, nature of the defect (e.g., peeling, blistering, drips, uneven coverage, missed areas)"Sub Standard Painted Surface" alone does not constitute sufficient particulars to evaluate the claim under the warranty policy. | Not Warrantable - see comments | Denied | 2026-04-02
68 | 2026-03-27 | Upstairs office | Sub standard painted surface. Large paint drip. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
69 | 2026-03-27 | Upstairs office | Sub standard painted surface. A properly painted surface (has consistent colour, appearance and cover) shall be provided on every exposed surface where a painted finish is specified and free from tool marks. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
70 | 2026-03-27 | Upper staircase walls | A properly painted surface (has consistent colour, appearance and cover) shall be provided on every exposed surface where a painted finish is specified and free from tool marks. | As per NOC dated 03/27/2026 |  | Insufficient information to determine warrantability. Please provide specific details of defect noted. | Not Warrantable - no defect noted | Denied | 2026-04-02
71 | 2026-03-27 | Primary En Suite Bathroom Ceiling | Primary En Suite Bathroom Ceiling Finishings - Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting. Not sanded at all and very rough. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
72 | 2026-03-27 | Primary En Suite Bathroom Ceiling | En Suite Bathroom Ceiling Finishings - nail pops. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
73 | 2026-03-27 | Primary En Suite Bathroom Ceiling | Primary En Suite Bathroom Ceiling Finishings - Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting.-- Tool marks. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
74 | 2026-03-27 | Ensuite | Primary En Suite Bathroom. Ceiling Finishings Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting. Rough patch and not sanded properly. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
75 | 2026-03-27 | Ensuite | Primary En Suite Bathroom. Ceiling Finishings Sub Standard. There are imperfections in the drywall or imperfections in the paint finishes. Recommend correction by filling and or sanding and repainting. Tools marks present. | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
76 | 2026-03-27 | Dining Room | Row of nail pops in dining room/kitchen | As per NOC dated 03/27/2026 |  |  | Investigation Required by Builder | In Progress
77 | 2026-03-27 | Upper Stairs | cracks | As per NOC dated 03/27/2026 |  | Please provide more information and specific location of the defect noted. | Not Warrantable - see comments | Denied | 2026-04-02